## Sheet1
ID | Risk Description | Probability | Impact | Risk Score
1 | Incomplete, ambiguous or incorrect requirements | 25% | 50% | 12.5%
2 | Use of outdated or unsuitable technology | 15% | 70% | 10.5%
3 | Technical issues during software development | 25% | 60% | 12%
4 | Integration with other systems not properly planned or executed | 15% | 80% | 8%
5 | Miscommunication with project stakeholders | 30% | 40% | 12%
6 | Unavailability of key stakeholders during project phase | 25% | 35% | 7%
7 | Legal or regulatory changes impacting project delivery | 5% | 80% | 4%
8 | Inadequate testing leading to errors and defects | 5% | 50% | 40%
9 | Delays in project and increased costs | 35% | 50% | 50%

## Sheet2
Risk Type | Risk Description | Impact | Likelihood | Mitigation Strategy
Requirements | Incomplete, ambiguous or incorrect requirements | High | Medium | Conduct regular meetings with stakeholders to ensure requirements are understood and documented clearly
Technology | Use of outdated or unsuitable technology | High | Low | Conduct regular technology assessments and ensure using the most appropriate technology for the project
Integration | Integration with other systems not properly planned or executed | Medium | High | Conduct regular integration testing to ensure all systems work seamlessly together
Quality | Inadequate testing leading to errors and defects | High | Medium | Conduct regular quality testing and use best practices in software development
Time and Cost | Delays in project and increased costs | High | High | Conduct regular progress monitoring, use agile methodologies, and have a contingency plan in place.
Communication | Unavailability of key stakeholders during project phase | High | High | Ensure clear communication channels, conduct regular progress monitoring, use agile methodologies, and have a contingency plan in place.
Licence | Legal or regulatory changes impacting project delivery | High | High | Stay up to date on regulatory changes, conduct regular progress monitoring, use agile methodologies, and have a contingency plan in place.
[5 empty] | likelihood | very high (75%-100%) | 5 |  |  |  | 5,6,7
High (50%-75%)
[6 empty] | Medium (20%-30%) |  | 1
Low (0-10%)
Very Low (0-10%)
[7 empty] | very low | low | medium | high | very high (75%-100%)
impact
Impact
[7 empty] | 5 |  |  |  | 5,6,7
1